## Jira Data
Issue Type | Key | Summary | Status | Created | Salesforce ID | Due date | Fix versions | Resolution | Client(s) | Labels | Client(s) | Labels | Client(s) | Clients
Bug | STOR-21244 | Mobile - FMS move in - send request button missing | Ready for Deployment | 2025-12-23 12:02 | a1iPJ000000t1zZYAQ | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  |  | edge-holiday-blitzen-2025;prio-software |  | edge-holiday-blitzen-2025;prio-software | West Coast | West Coast
Bug | STOR-21222 | Edge Trailing day reports: UI indicators (clock icon & date picker) not reflected at Corporate level after flipper enablement | Testing | 2025-12-23 10:44 |  | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  |  | edge-holiday-blitzen-2025;prio-software |  | edge-holiday-blitzen-2025;prio-software |  | Other
Bug | STOR-21209 | Task List - custom task for occupied unit doesn't attach | Ready for Deployment | 2025-12-21 11:57 | a1iPJ000000srLuYAI | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | StorageMart;West Coast | edge-holiday-blitzen-2025;prio-software | StorageMart;West Coast | edge-holiday-blitzen-2025;prio-software | West Coast | West Coast
Bug | STOR-21099 | Reversing payment as chargeback fails for moved out ledger | Ready for Deployment | 2025-12-13 08:15 | a1iPJ000000s7CbYAI | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | StorQuest | edge-holiday-blitzen-2025;prio-software | StorQuest | edge-holiday-blitzen-2025;prio-software | StorageMart | StorageMart
Bug | STOR-21074 | Replacement term ledger.insurance_premium_inc_tax showing wrong amount | Ready for Deployment | 2025-12-12 12:16 | a1iPJ000000s3TxYAI | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | StorageMart;West Coast | edge-holiday-blitzen-2025;otr_bugs_2026;prio-software | StorageMart | edge-holiday-blitzen-2025;otr_bugs_2026;prio-software | StorQuest | StorQuest
Bug | STOR-21049 | In mobile view switch facility button brings me to middle of list instead of top of list | Ready for Deployment | 2025-12-10 23:50 | a1iPJ000000sQwnYAE |  | Edge 2026.02.0 - 01/06/2026 |  |  | otr_bugs_2025;prio-software |  | edge-holiday-blitzen-2025;prio-software | Storage King | Storage King
Bug | STOR-21041 | API permissions removed | Ready for Deployment | 2025-12-10 12:01 | a1iPJ000000rlLlYAI | 2026-01-08 | Edge 2026.02.0 - 01/06/2026 |  |  | prio-software | National Storage Management | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;jl_bugs_2026;prio-software | West Coast | West Coast
Bug | STOR-21024 | UnInsured Endpoint is providing tenants with a future cancellation date for their coverage | Ready for Deployment | 2025-12-05 04:18 |  |  | Edge 2026.02.0 - 01/06/2026 |  |  |  | Storage King | edge-holiday-blitzen-2025;prio-software | National Storage Management | National Storage Management
Bug | STOR-20881 | Move Ins KPI report - autopay percent missing future move ins | Ready for Deployment | 2025-11-25 11:04 | a1iPJ000000q8azYAA | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  |  | edge-holiday-blitzen-2025;prio-software | Storage King | edge-holiday-blitzen-2025;prio-software | West Coast | West Coast
Bug | STOR-20864 | Inactive user attached to actions in tenant history. | Ready for Deployment | 2025-11-25 07:59 | a1iPJ000000q5wTYAQ | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | National Storage Management | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;jl_bugs_2026;prio-software | MyPlace | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;prio-software | West Coast | West Coast
Bug | STOR-20845 | Reservation Fee Credit upon Move In Leaving Open A/R | Ready for Deployment | 2025-11-24 08:36 | a1iPJ000000pxu5YAA | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | Storage King | edge-holiday-blitzen-2025;prio-software | Copper | edge-holiday-blitzen-2025;prio-software | Storage King | Storage King
Bug | STOR-20733 | Can't Void Auction Payments | Ready for Deployment | 2025-11-13 08:18 | a1iPJ000000ok7hYAA | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | Storage King | edge-holiday-blitzen-2025;prio-software | A-American | edge-holiday-blitzen-2025;prio-software | Columbia;West Coast | Columbia, West Coast
Bug | STOR-20688 | Corporate Merchandise Inventory Detail report - excel / csv export error | Ready for Deployment | 2025-11-08 09:42 | a1iPJ000000oIjJYAU | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | MyPlace | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;prio-software | Copper;StorageMart | edge-holiday-blitzen-2025;prio-software | A-American | A-American
Bug | STOR-20637 | Leads missing from Corporate level Lead Activity (Excel Export) report. | Ready for Deployment | 2025-11-04 07:56 | a1iPJ000000naQXYAY | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | Copper | edge-holiday-blitzen-2025;prio-software | West Coast | edge-holiday-blitzen-2025;prio-software | Public Storage Canada | Public Storage Canada
Bug | STOR-20568 | Surcharge fee persists after changing payment method when using Promotion. | Ready for Deployment | 2025-10-30 08:39 | a1iPJ000000n6nRYAQ | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | A-American | edge-holiday-blitzen-2025;prio-software | A-American | edge-holiday-blitzen-2025;prio-software | West Coast | West Coast
Bug | STOR-20538 | General page - Paid Through date not updating | Ready for Deployment | 2025-10-25 13:19 | a1iPJ000000mipxYAA | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | Copper;Go Store It;StorageMart | edge-holiday-blitzen-2025;prio-software |  | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;ins_dependency;prio-insurance;prio-software | West Coast | West Coast
Bug | STOR-20420 | When attempting a "balance" payment via the API it returns an "addons payment amount" error. | Ready for Deployment | 2025-10-15 08:31 | a1iPJ000000lSthYAE | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | West Coast | edge-holiday-blitzen-2025;prio-software | West Coast | edge-holiday-blitzen-2025;prio-software | All Aboard Storage | All Aboard Storage
Bug | STOR-20327 | Move Out failing - insurance item must belong to facility's insurance policy | Ready for Deployment | 2025-10-07 10:32 | a1iPJ000000kmODYAY | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | A-American;MyPlace | edge-holiday-blitzen-2025;prio-software | StorageMart;StorQuest | edge-holiday-blitzen-2025;jl_bugs_2026;prio-software | West Coast | West Coast
Bug | STOR-20236 | Mailhouse > View Confirmation failing to load | Ready for Deployment | 2025-09-30 15:54 | a1iPJ000000k7EbYAI | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | StorageMart | jl_bugs_2026;prio-software | All Aboard Storage | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;prio-software | Spartan | Spartan
Bug | STOR-20020 | Insurance Expiring tasks - updating insurance does not resolve event | Ready for Deployment | 2025-09-14 10:34 | a1iPJ000000iJmvYAE | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  |  | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;ins_dependency;prio-insurance;prio-software |  | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;prio-software | The Storage Mall | The Storage Mall
Bug | STOR-19951 | Unit Categories page goes blank when amenities condition is present | Ready for Deployment | 2025-09-12 17:15 | a1iPJ000000iBW1YAM | 2026-02-15 | Edge 2026.02.0 - 01/06/2026 |  |  | prio-software |  | edge-holiday-blitzen-2025;prio-software | Spartan | Spartan
Bug | STOR-19950 | Deleted units available for scheduled transfer | Ready for Deployment | 2025-09-13 15:43 | a1iPJ000000iIkPYAU | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | West Coast | edge-holiday-blitzen-2025;prio-software | All Aboard Storage | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;prio-software | Go Store It | Go Store It
Bug | STOR-19771 | Cannot move out tenant - BSON serialized type error | Ready for Deployment | 2025-08-27 10:37 | a1iPJ000000gex7YAA | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | StorageMart;StorQuest | edge-holiday-blitzen-2025;jl_bugs_2026;prio-software | Go Store It | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;prio-software | West Coast | West Coast
Bug | STOR-19624 | Last payment Column on Past due tab is incorrect for several tenants. | Ready for Deployment | 2025-08-19 07:41 | a1iPJ000000fnrBYAQ | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | All Aboard Storage | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;prio-software | West Coast | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;prio-software | StorEase | StorEase
Bug | STOR-19425 | Root Cause: Unable to Undo Delete for Units | Ready for Deployment | 2025-07-30 09:40 | a1iPJ000000eEc9YAE | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | National Storage Management | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;prio-software | West Coast | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;prio-software | West Coast | West Coast
Bug | STOR-19149 | Issue credits permission - per user / rental limit maximum | Ready for Deployment | 2025-06-28 13:01 | a1iPJ000000bFePYAU | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  |  | edge-holiday-blitzen-2025;prio-software |  | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;prio-software | West Coast | West Coast
Bug | STOR-19044 | Retail qty error from Bad debt write off | Ready for Deployment | 2025-06-23 07:48 | a1iPJ000000aVV7YAM | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | All Aboard Storage | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;prio-software | 10 Federal | edge-holiday-blitzen-2025;prio-software | StorEase | StorEase
Bug | STOR-18335 | Go Store It API Move in rate issue | Ready for Deployment | 2025-05-04 09:34 | a1iPJ000000V0zpYAC | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | Go Store It | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;prio-software | All Aboard Storage | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;jl_bugs_2026;prio-software | Go Store It | Go Store It
Bug | STOR-18310 | Future Move Ins - early check in rates incorrect | Ready for Deployment | 2025-04-30 11:55 | a1iPJ000000Ung1YAC | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | West Coast | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;prio-software |  | edge-holiday-blitzen-2025;prio-software | Go Store It | Go Store It
Bug | STOR-18270 | Default Role does not do anything (non-Storable ID) | Ready for Deployment | 2025-04-30 10:45 | a1iPJ000000UnRVYA0 | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | West Coast | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;prio-software |  | code_cs_email_sent;code_notified;code_notified_yellow;edge-holiday-blitzen-2025;prio-software | The Lock Up | The Lock Up
Bug | STOR-18136 | Schedule Transfer allows transferring to unrentable units | Ready for Deployment | 2025-04-19 10:57 | a1iPJ000000TxSvYAK | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | Spartan | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;prio-software |  |  | West Coast | West Coast
Bug | STOR-17626 | The v2 StorEDGE API is returning improperly encoded JSON responses | Ready for Deployment | 2025-03-10 10:52 | a1iPJ000000QxndYAC | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | 10 Federal | edge-holiday-blitzen-2025;prio-software |  |  |  | Other
Bug | STOR-17269 | Delinquency - insurance projected cancellation date not filling | Ready for PM Review | 2025-02-16 10:30 | a1iPJ000000PWHdYAO | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  | All Aboard Storage | edge-2025-blitz-top-30;edge-holiday-blitzen-2025;jl_bugs_2026;prio-software |  |  |  | Other
Bug | STOR-16711 | 500 error on Facility level refunds report, 11/14/24 | Ready for PM Review | 2024-12-20 15:13 | a1iPJ000000LyNlYAK | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  |  | edge-holiday-blitzen-2025;prio-software |  |  |  | Other
Bug | STOR-16167 | 500 error on facility level refunds report, 11/14/24, 11/15/24 | Ready for Deployment | 2024-12-04 11:05 | a1iPJ000000L8AfYAK | 2026-01-06 | Edge 2026.02.0 - 01/06/2026 |  |  | code_cs_email_sent;code_notified;code_notified_yellow;edge-holiday-blitzen-2025;prio-software |  |  |  | Other